## Project Management Plan
Week | Project Building CI/CD Pipeline | Difficulty | Effort
2023-05-01 | Project: Plan on Spreadsheet | Easy | 1 h
| Project: Plan on trello | Easy | 2 h
| Create Git Repo | Easy | 2 h
2023-05-08 | CI: Create the Cloud-Based Development Environment | Medium | 3 h
| CI: Create Project Scaffolding | Medium | 1,5 h
| CI: Local App Test | Easy | 0,5 h
| CI: SetUp Github Actions | Medium | 0,5 h
2023-05-15 | CI Replace yml code | Easy | 0,5 h
| CI: Verify Remote Tests for App pass | Medium | 1 h
| CD: Continuous Delivery on Azure | Medium | 3 h
2023-05-22 | CD: Making predictions | Medium | 0,5 h
| Project: Documentation (README, Screenshots, Architecture) | Medium | 4 h
2023-05-29 | Project: Demo Your Work (Video) | Hard | 3 h
Goals
2023-05-31 | Integration automated
Delivery automated
Deployed on Azure
Submit project